# HEALTHWATCH RUTLAND ACTION LOG MAY 2015  		PAPER B

| Item | Date | Action agreed and by whom | Progress narrative | No action taken |
| --- | --- | --- | --- | --- |
|  |  |  |  | Action being taken |
|  |  |  |  | Action completed |

| Minute 13.23.4 EMAS (Ambulance Services) | 12.12.13 | EMHW Chair representation on EMAS Board to be considered 14.01.14 | JF to report back on outcome to Steering Gp 30.01.14. Report given by JF to EMR 23/07 on three meetings of EMAS Board . Local ( Rutland) EMAS Group established under Chairmanship of Philip Herford and meets 22/08. EMAS will send sample data | J Fenelon ( Rutland) and J Moore ( Derby) nominated as participating observers on EMAS Board representing HW across EM. Good progress . Meeting of HW Chairs + CEO/Chair EMAS being arranged HWR Ambulance Task Group now established and first meeting held. EMAS/HW Collaboration paper being agreed with all HW in EM 25th March 2015 |
| --- | --- | --- | --- | --- |
| Minute 13.23.7 CQC | 12.12.13 | JF to meet Tim Birwhistle and receive CQC report | New Information Sharing Meeting established HWR represented by Judy Worthington Arrangements to be discussed at three HW chairs meeting to ensure effectiveness | New contact now established and meeting arranged Subsequently cancelled and being rearranged |

| 14.52.3 | Enter & View | To be operational 1st September 2014 | Training arranged for 20th August DBS contract now in place with Rutland County Council | Training undertaken on 20th August DBS applications now being processed |
| --- | --- | --- | --- | --- |
| 14.76 | BCT | Submit Rutland comments on BCT Plan to BCT Team | Comments sent and incorporated into final plan Comments put on website Press statement prepared | Comments of Rutland people submitted |

| 14.78d | Personal Budgets | Put on agenda for next meeting | Put on agenda for October meeting | Agenda 2111.14 Completed and JF on LLR GGroup |
| --- | --- | --- | --- | --- |
| 14.78d | Consultation | Meet CEO of GEM re consultation process | NHS England included All HW chairs in EM want to join meeting | Meeting being arranged - delay at GEM Still delayed since September . Discussed at EMHW meeting and agreed to give up trying. Poor impression gained by all. |
| 14.79 | Manifestoes | Keep manifestos under review re personal budgets | Too early for manifestos | Manifestos studied Good comparison from Kings Fund |
| 14.85 | GEM | Meeting of EM Chairs with GEM | Chase up | See above |
| 14.86 | SEND | Bring parent views on implementation back to Board | Review periodically to chase progress | Rutland Parent Carer Voice asked to report back as programme progresses |
| 14.87a | Governance policies | Put on website as refreshed | Bring to Board for approval | three policies approved in March 2015 still outstanding from Website |
| 14.87c | Enter & View | Prepare Policy Arrange first trial Enter & View | Bart Taylor Harris is assisting implementation | System in place and first Enter & View undertaken. Second being planned. |

| 14.87d | Dementia Project | Complete Pathway Mapping Complete Patient/carer interviews start arranging Spring Conference | Hold further events to complete mapping Recruit & Train " Listeners Recruit Patients and Carers | Medical Events 19.11.14 & 20.11.14 Care Home Event 12.12.14 Events being attended to recruit further patients and carers Feedback Session held onr 22.04.15 |
| --- | --- | --- | --- | --- |
| 14.87.e | Communication | Extend hard copies of bulletins to those without email Use the good offices of VAR Social Car Scheme to distribute leaflets | Update distribution list with addresses Restock literature Contact J Smith re Social Car Scheme | Ali Burrow Smith has actioned. Only rwo requests for hard copies. |
| 14.88a | Better Care Fund | Work with RCC to help input Public/ patient Views into projects | Ali Burrow-Smith to lead | Collaboration agreed |
| 14.88b | Complaints | LLR Complaints Group reconvened | Send HWR Representative to join group | David Henson attended 24.11.14 |
| 14.88d | Pharmaceutical Assessment | Public Consultation | Prepare views of HWR based on public's input | On agenda for 21.11.14 Views submitted to RCC |
| 14.788e | EMAS | Access Data to sent quarterly | HWR Ambulance Task Group to take forward action with local EMAS Team | Ambulance Task group will consider at next meeting on 08.04.15. T Slater to attend |
| 14.88f | Cancer Targets UHL | Take up with UHL ( DH) Take up with CCG ( JF) |  | JF and DH still pursuing but no perceptible progress by May 2015 |
| 14.89 | Hard to reach groups | Include Men in groups to be targeted | Ali Burrow-Smith to take forward with plan of listening events | Will be programmed when appropriate groups identified |
| 15.7.5 | Young People's Team | Present findings of survey ro all involved agencies | Results presented by Prof Fitchett of Leicester University | Results well received and agreement to look at solutions as Phase2 |
| 15.7.9 | Emergency Ambulances | EMAS/HWR Collaboration Group | Establish regular working party | New meeting being chased . Now scheduled for 08.04.15 |
| 15.7.10 | Minor Injuries | Contract awarded to N Doctors | Presentation by N Doctors given | David Henson providing PPI input into Marketing Programme |
| 15.7.11 | " We are Listening " | 2015-6 programme being finalised |  | Schedule to be tabled at Board 20.03.15 after agreement with RCC . Still being developed May 2015 |
| 15.7.12 | Comms | Review membership and introduce double opt in system Website improvements |  | Ali Burrow Smith to lead Ali Burrow Smith to lead |
| 15.7.14 | Volunteers | Support & expansion | Develop recruitment and support processes | Ali Burrow Smith to lead |
| 15.17.a | Volunteer Skills Audit | Due for completion by end March 2015 by ABS |  | Results awaited |
| 15.17.b | First Enter & View | Draft report sent to providers concerned |  | Comments awaited |
| 15.17.d | Young People's Team | Multiple activity underway to define service required and seek agreement with the commissioners |  | Project progressing well with whole Young People's Team participating |
| 15.17.e | " We are Listening" | Joint programme scheduled for May /June 2015 |  | Final schedule awaited |
| 15.17.e | Community Agents | Collaboration being pursued |  | Sue Renton to join ops group meeting Joint work to synchronise signposting service |
| 15.17.i | Recruitment of volunteers | combination of recruitment and profile raising |  | Profile raising see 15.05.15 agenda Volunteer recruitment being worked on |
| 15.17.i | Schedule of meetings on website |  |  | Full meeting schedule required |
| 15.18a Forward development Plan | Plan agreed and returned to Ops Group for implementation |  |  | Work to be undertaken through Ops Group |
| 15.18.b | Public Engagement Plan | Bring schedule of meetings across public bodies back as complete schedule but in meantime put agreed dates/venues on website |  | In progress |
| 15.18.f | EMAS | Collaborate in implementing new agreement |  | In progress |
| 15.18.g | ARIVA | Consider further investigation of patient experience |  | Refer to Ops Group |