- HEALTHWATCH RUTLAND ACTION LOG NOVEMBER 2014  		PAPER B

| Item | Date | Action agreed and by whom | Progress narrative | No action taken |
| --- | --- | --- | --- | --- |
|  |  |  |  | Action being taken |
|  |  |  |  | Action completed |
| Representation | 02.08.13 | To keep representation under review | Fiona Kerr and David Henson taking forward membership and TOR of Task Groups and Operational Group to address workload | Progressing .Operations Group has had four meetings and Task Groups are developing. Interchange between groups important Keep progress under review |
| Minute 13.23.3 Clwyd LLR Task Group | 12.12.13 | JF will pull together all of the views and share them with the working group prior to LAT meeting | Comments incorporated in LLR draft and shared with LAT complaints Team . Single point of contact agreed by CEOs as part of BCT | New Chair of LLR Complaints Group appointed ( Helen Childs) to take implementation forward. |
|  |  | HWE submitting national report to parliament with PR campaign | HWE National Launch 16.10.14 | LLR Complaints Group will meet 24.11.14 . David Henson will represent HWR |
| Minute 13.23.4 EMAS (Ambulance Services) | 12.12.13 | EMHW Chair representation on EMAS Board to be considered 14.01.14 | JF to report back on outcome to Steering Gp 30.01.14. Report given by JF to EMR 23/07 on three meetings of EMAS Board . Local ( Rutland) EMAS Group established under Chairmanship of Philip Herford and meets 22/08. EMAS will send sample data | J Fenelon ( Rutland) and J Moore ( Derby) nominated as participating observers on EMAS Board representing HW across EM. Good progress . Meeting of HW Chairs + CEO/Chair EMAS being arranged HWR Ambulance Task Group now established and first meeting held. |
| Minute 13.23.7 CQC | 12.12.13 | JF to meet Tim Birwhistle and receive CQC report | - New Information Sharing Meeting established - HWR represented by Judy Worthington - Arrangements to be discussed at three HW chairs meeting to ensure effectiveness | Under review with 3 HW chairs and Judy Worthington . Meeting chased |
| Minute 14.32.4 | Representation | - JF asked the group to look at the list over the next few weeks and identify areas that we need to be involved in, in the future. - JF to agree stance on Better Care Together and relation to Rutland County Council in terms of representation. - Ann Williams to continue to develop the strategy for working with Young People. - CS to look at how we can have meaningful involvement in work with Peterborough. | Structure and roles of HWR taken forward and brought to Board meeting 02/04 for approval HWR Manager mandated to define and take forward Task Gp and Operational Group arrangements Awayday with volunteers envisaged for Autumn | Review workload on volunteers in Autumn - Half Year Stocktake undertaken |

| Minute 14.43.4 | Budget | - Contract negotiations with Rutland County Council | - Discussions commenced on Tender process - Attempts to secure set up funds from VAL | Contract discussions ongoing VAL set up funds being pursued ( BR)- awaiting HWL report |
| --- | --- | --- | --- | --- |
| 14.44.2 | EMAS | - Keep members informed on development of rural role | - Keep members informed - Find volunteer to represent HWR | Data now being supplied Results are starting to improve |
| - 14.52.2 | Home working Policy | - To be finalised and promulgated | - Being revised by Fiona Kerr | Ongoing |
| - 14.52.3 | Enter & View | - To be operational 1st September 2014 | - Training arranged for 20th August - DBS contract now in place with Rutland County Council | Training undertaken on 20th August DBS applications being processed |
| - 14.76 | BCT | - Submit Rutland comments on BCT Plan to BCT Team | - Comments sent and incorporated into final plan - Comments put on website - Press statement prepared | Comments of Rutland people submitted |
| - 14.77b | Governance Policies | - Governance policies revised | - Submitted to October meeting by Fiona Kerr | Revised policies considered by Board on 21.11.14 |
| - 14.78d | Personal Budgets | - Put on agenda for next meeting | - Put on agenda for October meeting | Agenda 21.11.14 |
| - 14.78d | Consultation | - Meet CEO of GEM re consultation process | - NHS England included - All HW chairs in EM want to join meeting | Meeting being arranged - delay at GEM |
| - 14.79 | Manifestoes | - Keep manifestos under review re personal budgets | - Too early for manifestos | Keep under review ar election approaches |
| 14.85 | CQC | - Chase Tim Birtwhistle | - Chased again | Chased |
| 14.85 | EMAS | - Meet Chair/CEO EMAS 12.11.14 | - Report back to Board on meeting | On agenda 21.11.14 |
| 14.85 | GEM | - Meeting of EM Chairs with GEM | - Chase up | Chased |
| 14.86 | SEND | - Bring parent views on implementation back to Board | - Review periodically to chase progress | Rutland Parent Carer Voice asked to report back as programme progresses |
| 14.87a | Governance policies | - Put on website as refreshed | - Bring to Board for approval | Put on agenda 21.11.14 David Henson is drafting two outstanding policies |
| - 14.87b | Assurance reports | - circulate assurance reports to Board | - Ali Burrow - Smith to forward | To be forwarded when all November reports in |
| - 14.87c | Enter & View | - Prepare Policy - Arrange first trial Enter & View | - Bart Taylor Harris is assisting implementation | Being progressed |
| - 14.87d | Dementia Project | - Complete Pathway Mapping - Complete Patient/carer interviews - start arranging Spring Conference | - Hold further events to complete mapping - Recruit & Train " Listeners - Recruit Patients and Carers | - Medical Events 19.11.14 & 20.11.14 - Care Home Event 12.12.14 - Events being attended to recruit further patients and carers |
| - 14.87.e | Communication | - Extend hard copies of bulletins to those without email - Use the good offices of VAR Social Car Scheme to distribute leaflets | - Update distribution list with addresses - Restock literature - Contact J Smith re Social Car Scheme | - Ali Burrow Smith to action |
| - 14.88a | Better Care Fund | - Work with RCC to help input Public/ patient Views into projects | - Ali Burrow-Smith to lead | Collaboration agreed |
| - 14.88b | Complaints | - LLR Complaints Group reconvened | - Send HWR Representative to join group | David Henson will attend 24.11.14 |
| - 14.88d | Pharmaceutical Assessment | - Public Consultation | - Prepare views of HWR based on public's input | On agenda for 21.11.14 .Agree views to be submitted to RCC |
| - 14.788e | EMAS | - Access Data to sent quarterly | - HWR Ambulance Task Group to take forward action with local EMAS Team | Ambulance Task group will consider at next meeting |
| - 14.88f | Cancer Targets UHL | - Take up with UHL ( DH) - Take up with CCG ( JF) |  | JF and DH to give verbal update at 21.11.14 meeting |
| - 14.89 | Hard to reach groups | - Include Men in groups to be targeted | - Ali Burrow-Smith to take forward with plan of listening events | Will be programmed when appropriate groups identified |