- HEALTHWATCH RUTLAND ACTION LOG JULY 2015  		PAPER C

| Item | Date | Action agreed and by whom | Progress narrative | No action taken |
| --- | --- | --- | --- | --- |
|  |  |  |  | Action being taken |
|  |  |  |  | Action completed |

| Minute 13.23.4 EMAS (Ambulance Services) | 12.12.13 | EMHW Chair representation on EMAS Board to be considered 14.01.14 | JF to report back on outcome to Steering Gp 30.01.14. Report given by JF to EMR 23/07 on three meetings of EMAS Board . Local ( Rutland) EMAS Group established under Chairmanship of Philip Herford and meets 22/08. EMAS will send sample data | HWR Ambulance Task Group now established and two meetings held. EMAS/HW Collaboration Group established. P Hurford attends for HWR Data still awaited |
| --- | --- | --- | --- | --- |
| Minute 13.23.7 CQC | 12.12.13 | JF to meet Tim Birwhistle and receive CQC report | - New Information Sharing Meeting established - HWR represented by Judy Worthington - Arrangements to be discussed at three HW chairs meeting to ensure effectiveness | Formal Meeting with Michelle Hurst of CQC held. Positive exchange of information |

| - 14.76 | BCT | - Submit Rutland comments on BCT Plan to BCT Team | - Comments sent and incorporated into final plan - Comments put on website - Press statement prepared | Comments of Rutland people submitted |
| --- | --- | --- | --- | --- |

| - 14.78d | Personal Budgets | - Put on agenda for next meeting | - Put on agenda for October meeting | Agenda 2111.14 Completed and JF on LLR GGroup |
| --- | --- | --- | --- | --- |
| 14.86 | SEND | - Bring parent views on implementation back to Board | - Review periodically to chase progress | Rutland Parent Carer Voice asked to report back as programme progresses |
| 14.87a | Governance policies | - Put on website as refreshed | - Bring to Board for approval | three policies approved in March 2015 still outstanding from Website |
| - 14.87c | Enter & View | - Prepare Policy - Arrange first trial Enter & View | - Bart Taylor Harris is assisting implementation | Two Enter & Views undertaken to date . Forward programme being planned. |

| - 14.87d | Dementia Project | - Complete Pathway Mapping - Complete Patient/carer interviews - start arranging Spring Conference | - Hold further events to complete mapping - Recruit & Train " Listeners - Recruit Patients and Carers | - Medical Events 19.11.14 & 20.11.14 - Care Home Event 12.12.14 - Events being attended to recruit further patients and carers - Feedback Session held on 22.04.15 |
| --- | --- | --- | --- | --- |
| - 14.87.e | Communication | - Extend hard copies of bulletins to those without email - Use the good offices of VAR Social Car Scheme to distribute leaflets | - Update distribution list with addresses - Restock literature - Contact J Smith re Social Car Scheme | - Ali Burrow Smith has actioned. Only two requests for hard copies. |
| - 14.88a | Better Care Fund | - Work with RCC to help input Public/ patient Views into projects | - Ali Burrow-Smith to lead | Collaboration agreed |
| - 14.88b | Complaints | - LLR Complaints Group reconvened | - Send HWR Representative to join group | David Henson attended 24.11.14 |
| - 14.88d | Pharmaceutical Assessment | - Public Consultation | - Prepare views of HWR based on public's input | On agenda for 21.11.14 Views submitted to RCC |
| - 14.788e | EMAS | - Access Data to sent quarterly | - HWR Ambulance Task Group to take forward action with local EMAS Team | Ambulance Task group will consider at next meeting on 08.04.15. T Slater to attend |
| - 14.88f | Cancer Targets UHL | - Take up with UHL ( DH) - Take up with CCG ( JF) |  | JF and DH still pursuing but no perceptible progress by May 2015. Raised at QSG 03.07.15 as major concern |
| - 14.89 | Hard to reach groups | - Include Men in groups to be targeted | - Ali Burrow-Smith to take forward with plan of listening events | Will be programmed when appropriate groups identified and " We are Listening programme completed |
| - 15.7.5 | Young People's Team | - Present findings of survey ro all involved agencies | - Results presented by Prof Fitchett of Leicester University | Results well received and agreement to look at solutions as Phase2 |
| - 15.7.9 | Emergency Ambulances | - EMAS/HWR Collaboration Group | - Establish regular working party | New meeting being chased . Now scheduled for 08.04.15 |
| - 15.7.10 | Minor Injuries | - Contract awarded to N Doctors | - Presentation by N Doctors given | David Henson providing PPI input into Marketing Programme |
| - 15.7.11 | " We are Listening " | - 2015-6 programme being finalised |  | Schedule to be tabled at Board 20.03.15 after agreement with RCC . Still being developed July 2015. |
| - 15.7.12 | Comms | - Review membership and introduce double opt in system - Website improvements |  | Ali Burrow Smith to lead Ali Burrow Smith to lead |
| - 15.7.14 | Volunteers | - Support & expansion | - Develop recruitment and support processes | Ali Burrow Smith to lead |
| - 15.17.a | Volunteer Skills Audit | - Due for completion by end March 2015 by ABS |  | Results awaited |
| - 15.17.b | First Enter & View | - Draft report sent to providers concerned |  | Enter & View of Rutland Memorial Published |
| - 15.17.d | Young People's Team | - Multiple activity underway to define service required and seek agreement with the commissioners |  | Project progressing well with whole Young People's Team participating. Paper to Health & Wellbeing Board 23.07.15 |
| - 15.17.e | " We are Listening" | - Joint programme scheduled for May /June 2015 |  | Final schedule awaited |
| - 15.17.e | Community Agents | - Collaboration being pursued |  | - Sue Renton to join ops group meeting - Joint work to synchronise signposting service |
| - 15.17.i | Recruitment of volunteers | - combination of recruitment and profile raising |  | - Volunteer recruitment being worked on |
| - 15.17.i | Schedule of meetings on website |  |  | Full meeting schedule required |
| - 15.18a Forward development Plan | Plan agreed and returned to Ops Group for implementation |  |  | Work to be undertaken through Ops Group |
| - 15.18.b | Public Engagement Plan | - Bring schedule of meetings across public bodies back as complete schedule but in meantime put agreed dates/venues on website |  | In progress |
| - 15.18.f | EMAS | - Collaborate in implementing new agreement |  | In progress |
| - 15.18.g | ARRVA | - Consider further investigation of patient experience |  | Refer to Ops Group |
|  | Skills Audit for 30.03.15 | - Data sought |  | Skills data sought from Vplunteers |